## Proc. Plan - WORKS
Annex - III (b)
Ref: PPR, 2008
Total procurement plan for development project/programme
Project Name: |  | Rehabilitation/Renovation of Electrical and Arboriculture Work of Planning Commission campus at sher-e-Bangla Nagar, Dhaka.
Ministry/Division: |  | Ministry of Planning, Planning Division
Agency: |  | Planning Division Public Works Department (PWD) | [6 empty] | Total GoB (FE): 703.1600000000001(0)
Procuring Entity Name and Code: |  | Procuring Entity | [6 empty] | Total PA (RPA): 0(0)
Project/Programme Code: |  | Project/Programme Code | [6 empty] | Others (FE): 0(0)
Package No. | Description of Procurement Package as per DPP/TPP WORKS | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estd. Cost (In lakh tk) | Invitation for Prequal (if applicable) | Invitation for Tender | Signing of Contract | Completion of Contract
1-wd | Supply and Replacement of damaged underground main cable of NEC building and Necessary work. | 0 | 0 | OTM(NCT) | SE | GOB | 80.12 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
2-wd | Supply and Replacement of damaged Service cable of Building No 3,4,5 & 6 | 0 | 0 | OTM(NCT) | SE | GOB | 8.88 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
3-wd | Supply and Replacement of damaged air cooler of different capacities in planning Division | 0 | 0 | OTM(NCT) | SE | GOB | 98.19 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
4-wd | Supply and Replacement of damaged HT Switch gear, LT switch Gear, PFI and necessary works of 400KVA Sub-Station. | 0 | 0 | OTM(NCT) | SE | GOB | 16.64 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
5-wd | Supply and Replacement of damaged Duct pump motor set of 90 Ton central A/C and necessary work | 0 | 0 | OTM(NCT) | SE | GOB | 25.31 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
6-wd | Supply and Replacement of damaged sub main power line, control switch SPDB and necessary work of building No-l-18(GF to 2nd F) of planning Commission complex. | 0 | 0 | OTM(NCT) | SE | GOB | 68.93 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
7-wd | Supply and Replacement of Oil in X-former, different panel board and other necessary works. | 0 | 0 | OTM(NCT) | SE | GOB | 15.59 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
8-wd | Supply and Replacement of Metal halide light and necessary works | 0 | 0 | OTM(NCT) | SE | GOB | 12.89 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
9-wd | Supply and Replacement of 2000KVA Sub-Station in lieu of 800 KVA sub-Station and other necessary works | 0 | 0 | OTM(NCT) | SE | GOB | 103.33 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
10-wd | Supply and Installation of L.C work of different building in planning commission campus | 0 | 0 | OTM(NCT) | SE | GOB | 44.58 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
11-wd | Supply and Installation of Security light and necessary work in planning Commission campus. | 0 | 0 | OTM(NCT) | SE | GOB | 19.15 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
12-wd | Supply and Installation of damaged main service cable and necessary work west side Building No 3,4,5,6,11,12 of planning Commission campus. | 0 | 0 | OTM(NCT) | SE | GOB | 59.38 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
13-wd | Supply and Installation of damaged main service cable and necessary (work of East side Building No 1,2,7,8,9,10,15,16 of planning Commission | 0 | 0 | OTM(NCT) | SE | GOB | 64.21 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2015-12-30
14-wd | Arboriculture work of planning commission Campus | 0 | 0 | OTM(NCT) | SE | GOB | 38 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2016-03-20
15-wd | Supply and Installation of CCTV camera in Planning commission Supply and Installation of CCTV camera in Planning commission | 0 | 0 | OTM(NCT) | SE | GOB | 39.76 | 0000-00-00 | 2015-04-09 | 2015-06-10 | 2016-03-20
Grand Total | [6 empty] | 694.96