## Proc. Plan - SERVICES
Annex - III (c)
Ref: PPR, 2008
Total procurement plan for development project/programme
Project Name: |  | 4-Laning of Dhaka Chittagong National Highway Project.
Ministry/Division: |  | Roads Division
Agency: |  | Roads and Highways Department, Bangladesh | [6 empty] | Total GoB (FE): 216838.41(0)
Procuring Entity Name and Code: |  | Procuring Entity | [6 empty] | Total PA (RPA): 0(0)
Project/Programme Code: |  | Project/Programme Code | [6 empty] | Others (FE): 0(0)
Package No. | Description of Procurement Package as per DPP/TPP SERVICES | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estd. Cost (In lakh tk) | Invitation for EOI (if applicable) | Issue of RFP | Signing of Contract | Completion of Contract
4-LP/S-1 | Design & Supervisions 4-Laning ol Dhaka- Chittagong Highway (Daudkandi-Chittagong Section) | MM | 2430.5 | QCBS(NCT) | CCGP | GOB | 3267.19 | 2005-07-01 | 2008-08-01 | 2006-04-30 | 2011-12-31
4-LP/S-2 | Outsourcing of Man power | MM | 3360 | QCBS(NCT) | CCGP | GOB | 229.11 | 2008-03-31 | 2008-04-01 | 2008-06-01 | 2012-12-31
Grand Total | [6 empty] | 3496.3