## Proc. Plan - WORKS
Annex - III (b)
Ref: PPR, 2008
Total procurement plan for development project/programme
Project Name: |  | 4-Laning of Dhaka Chittagong National Highway Project.
Ministry/Division: |  | Roads Division
Agency: |  | Roads and Highways Department, Bangladesh | [6 empty] | Total GoB (FE): 216838.41(0)
Procuring Entity Name and Code: |  | Procuring Entity | [6 empty] | Total PA (RPA): 0(0)
Project/Programme Code: |  | Project/Programme Code | [6 empty] | Others (FE): 0(0)
Package No. | Description of Procurement Package as per DPP/TPP WORKS | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estd. Cost (In lakh tk) | Invitation for Prequal (if applicable) | Invitation for Tender | Signing of Contract | Completion of Contract
Contract PackageNo.1 | Daudkandi Toll Plaza to Kutumbpur | km | 22 | OTM(NCT) | CCGP | GOB | 22349.44 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.2 | Kutumbpur to Start of Comilla Bypass | km | 23 | OTM(NCT) | CCGP | GOB | 20554.18 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.3 | Start ol Comilla Bypass to End ol Comilla Bypass | km | 21 | OTM(NCT) | CCGP | GOB | 20251.26 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.4 | End of Comilla Bypass to Batisha | km | 20 | OTM(NCT) | CCGP | GOB | 16913.49 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.5 | Batish to Mohipal | km | 20 | OTM(NCT) | CCGP | GOB | 16649.42 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.6 | Mohipal to Start of Dhum Ghat Bridge | km | 19.916 | OTM(NCT) | CCGP | GOB | 16186.7 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.7 | Start of Dhum Ghat Bridge to Mirersarai Bazar | km | 15.667 | OTM(NCT) | CCGP | GOB | 13698.68 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.8 | Mirarsaral Bazar to Paunchashita Bazar | km | 18 | OTM(NCT) | CCGP | GOB | 15828.25 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.9 | Paunchashila Bazat to End of Kumira Bypass | km | 18 | OTM(NCT) | CCGP | GOB | 16676.77 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.10 | End of Kumira Bypass to Alanker Cinema Hall (Chittagong) | km | 16.44 | OTM(NCT) | CCGP | GOB | 17180.28 | 0000-00-00 | 2008-03-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.11 | Bridge Contract No B-1 | nos | 4 | OTM(NCT) | CCGP | GOB | 15519.8 | 0000-00-00 | 2008-06-01 | 2008-08-15 | 2011-12-31
Contract PackageNo.12 | Budge Contract No. U-2 | Nos | 5 | OTM(NCT) | CCGP | GOB | 8083.94 | 0000-00-00 | 2008-06-01 | 2008-08-15 | 2011-12-31
Grand Total | [6 empty] | 199892.21