## Proc. Plan - WORKS
Annex - III (b)
Ref: PPR, 2008
Total procurement plan for development project/programme
Project Name: |  | Aid Effectiveness Project for ERD
Ministry/Division: |  | Ministry of Agriculture
Agency: |  | Bangladesh Institute of Administration & Management Foundation (BIAM) Bangladesh Institute of Nuclear Agriculture (BINA) | [6 empty] | Total GoB (FE): 19.03(21.43)
Procuring Entity Name and Code: |  | Procuring Entity | [6 empty] | Total PA (RPA): 37(29)
Project/Programme Code: |  | Project/Programme Code | [6 empty] | Others (FE): 11.77(11.75)
Package No. | Description of Procurement Package as per DPP/TPP WORKS | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estd. Cost (In lakh tk) | Invitation for Prequal (if applicable) | Invitation for Tender | Signing of Contract | Completion of Contract
xxxx | sdfas | 44 | 1 | TSTM(INT) |  |  | 55 | 2014-10-08 | 2014-10-21 | 2014-10-21 | 2014-10-21
4 | asdfa | 4 | 1 | RFQM(NCT) |  |  | 5 | 2014-10-15 | 2014-10-21 | 2014-10-21 | 2014-10-21
43 | adsadf | sdf | 12 | DPM(NCT) | GoB | UNDP | 12 | 2014-10-22 | 2014-10-21 | 2014-10-21 | 2014-10-21
Grand Total | [6 empty] | 72